## Sheet1
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Airline Reservation System | 1 | Login | Analysis | Requirement Analysis | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2018-06-30 | 2018-06-30 | 2.4 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2015-10-12 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | K.S.Charumathi | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | K.S.Charumathi | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | K.Yaswanth | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | K.Yaswanth | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | S.Shruthi | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | K.Yaswanth | N/A
|  |  | Build | Coding | 6 | 2018-07-06 | 2015-10-19 | 7 | 2018-07-06 | 2015-10-19 | K.NavyaSantoshi | Completed
|  |  |  | Code Self Review | 2.5 | 2015-10-20 | 2015-10-20 | 2.5 | 2015-10-20 | 2015-10-20 | K.NavyaSantoshi | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 7 | 2018-07-06 | 2015-10-19 | K.NavyaSantoshi | Completed
|  |  |  | Rework | 1.5 | 2015-10-20 | 2015-10-20 | 1.5 | 2015-10-20 | 2015-10-20 | D.LakshmiNagaratnam | Completed
|  |  |  | Code Peer Review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | S.Shruthi | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | S.Shruthi | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | K.S.Charumathi | Completed
|  |  |  | Rework | 1 | 2015-10-21 | 2015-10-21 | 1.5 | 2015-10-21 | 2015-10-21 | K.Yaswanth | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 4 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1.5 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 3 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 1 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 55.6 |  | Total Actual Hrs: | 38.2 |  |  |  | Completed
Airline Reservation System | 2 | Register User | Analysis | Requirement Analysis | 2.4 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2018-06-30 | 2018-06-30 | 2.1 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2018-07-03 | 2018-07-03 | 1 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 | 12 | 2018-07-04 | 2018-07-04 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 | 12 | 2018-07-05 | 2018-07-05 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 | 1.5 | 2018-07-04 | 2018-07-05 | Prabhjot Singh | Completed
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 | 0.5 | 2018-07-04 | 2018-07-05 | Balaji Veerappan | Completed
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 | 0.8 | 2018-07-05 | 2018-07-06 | Prabhjot Singh | Completed
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 | 0.5 | 2018-07-05 | 2018-07-06 | Balaji Veerappan | Completed
|  |  | Build | Coding | 11 | 2018-07-06 | 2015-10-19 | 13 | 2018-07-06 | 2015-10-19 | Balaji Veerappan | Completed
|  |  |  | Code Self Review | 5 | 2015-10-20 | 2015-10-20 | 4 | 2015-10-20 | 2015-10-20 | Balaji Veerappan | Completed
|  |  |  | Self Testing | 5 | 2018-07-06 | 2015-10-19 | 5 | 2018-07-06 | 2015-10-19 | Balaji Veerappan | Completed
|  |  |  | Rework | 3 | 2015-10-20 | 2015-10-20 | 2.5 | 2015-10-20 | 2015-10-20 | Balaji Veerappan | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 3 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 2.5 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Balaji Veerappan | Completed
|  |  |  | Rework | 2 | 2015-10-21 | 2015-10-21 | 1.5 | 2015-10-21 | 2015-10-21 | Balaji Veerappan | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 2 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 2.5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 66.6 |  | Total Actual Hrs: | 74 |  |  |  | Completed
Airline Reservation System | 3 | Add Bookings | Analysis | Requirement Analysis | 1.5 | 2018-06-30 | 2018-06-30 | 1.5 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.7 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Nafeez Virani | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Nafeez Virani | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Balaji Veerappan | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Nafeez Virani | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Balaji Veerappan | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Nafeez Virani | N/A
|  |  | Build | Coding | 12 | 2018-07-06 | 2015-10-19 | 14.5 | 2018-07-06 | 2015-10-19 | Nafeez Virani | Completed
|  |  |  | Code Self Review | 5 | 2015-10-20 | 2015-10-20 | 5 | 2015-10-20 | 2015-10-20 | Nafeez Virani | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 5.5 | 2018-07-06 | 2015-10-19 | Nafeez Virani | Completed
|  |  |  | Rework | 3 | 2015-10-20 | 2015-10-20 | 4 | 2015-10-20 | 2015-10-20 | Nafeez Virani | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 2.5 | 2015-10-21 | 2015-10-21 | Balaji Veerappan | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Balaji Veerappan | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Rework | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3.6 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 1 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 66.7 |  | Total Actual Hrs: | 51.3 |  |  |  | Completed
Airline Reservation System | 4 | View Flights | Analysis | Requirement Analysis | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2018-06-30 | 2018-06-30 | 2.4 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Pritika Sharma | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Anoop Singh Jaswal | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Anoop Singh Jaswal | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Pritika Sharma | N/A
|  |  | Build | Coding | 10 | 2018-07-06 | 2015-10-19 | 10 | 2018-07-06 | 2015-10-19 | Pritika Sharma | Completed
|  |  |  | Code Self Review | 2 | 2015-10-20 | 2015-10-20 | 2.5 | 2015-10-20 | 2015-10-20 | Pritika Sharma | Completed
|  |  |  | Self Testing | 5 | 2015-10-16 | 2015-10-19 | 5.5 | 2018-07-06 | 2015-10-19 | Pritika Sharma | Completed
|  |  |  | Rework | 1 | 2015-10-20 | 2015-10-20 | 1.5 | 2015-10-20 | 2015-10-20 | Pritika Sharma | Completed
|  |  |  | Code Peer Review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1.75 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1.25 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Rework | 1 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 3.2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 1 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 57.7 |  | Total Actual Hrs: | 39.9 |  |  |  | Completed
Airline Reservation System | 5 | Cancel Bookings | Analysis | Requirement Analysis | 2.1 | 2018-06-30 | 2018-06-30 | 2.1 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2018-06-30 | 2018-06-30 | 2.1 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Anoop Singh Jaswal | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Anoop Singh Jaswal | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Rahul Yadav | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Anoop Singh Jaswal | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Rahul Yadav | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Anoop Singh Jaswal | N/A
|  |  | Build | Coding | 13 | 2018-07-06 | 2015-10-19 | 10 | 2018-07-06 | 2015-10-19 | Anoop Singh Jaswal | Completed
|  |  |  | Code Self Review | 5 | 2015-10-20 | 2015-10-20 | 5 | 2015-10-20 | 2015-10-20 | Anoop Singh Jaswal | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 6.6 | 2018-07-06 | 2015-10-19 | Anoop Singh Jaswal | Completed
|  |  |  | Rework | 3 | 2015-10-20 | 2015-10-20 | 3.2 | 2015-10-20 | 2015-10-20 | Anoop Singh Jaswal | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 3 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Peer Testing | 2 | 2015-10-21 | 2015-10-21 | 2.8 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1.5 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Rework | 2 | 2015-10-21 | 2015-10-21 | 2.5 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3.5 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 2 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 4.5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 1 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 69.6 |  | Total Actual Hrs: | 51.8 |  |  |  | Completed
Airline Reservation System | 6 | Add Flight | Analysis | Requirement Analysis | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2018-06-30 | 2018-06-30 | 2.1 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2018-07-03 | 2018-07-03 | 0.9 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Pritika Sharma | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Anoop Singh Jaswal | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Anoop Singh Jaswal | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Pritika Sharma | N/A
|  |  | Build | Coding | 10 | 2018-07-06 | 2015-10-19 | 11.3 | 2018-07-06 | 2015-10-19 | Pritika Sharma | Completed
|  |  |  | Code Self Review | 2 | 2015-10-20 | 2015-10-20 | 2.5 | 2015-10-20 | 2015-10-20 | Pritika Sharma | Completed
|  |  |  | Self Testing | 5 | 2018-07-06 | 2015-10-19 | 5 | 2015-10-16 | 2015-10-19 | Pritika Sharma | Completed
|  |  |  | Rework | 1 | 2015-10-20 | 2015-10-20 | 1 | 2015-10-20 | 2015-10-20 | Pritika Sharma | Completed
|  |  |  | Code Peer Review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Anoop Singh Jaswal | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Rework | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 4 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 4 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 56.8 |  | Total Actual Hrs: | 40.2 |  |  |  | Completed
Airline Reservation System | 7 | Caancel Flight | Analysis | Requirement Analysis | 1.5 | 2018-06-30 | 2018-06-30 | 2.7 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.1 | 2018-06-30 | 2018-06-30 | 2.1 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Prabhjot Singh | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Prabhjot Singh | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Nafeez Virani | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Prabhjot Singh | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Nafeez Virani | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Prabhjot Singh | N/A
|  |  | Build | Coding | 6 | 2018-07-06 | 2015-10-19 | 6 | 2018-07-06 | 2015-10-19 | Prabhjot Singh | Completed
|  |  |  | Code Self Review | 2 | 2015-10-20 | 2015-10-20 | 2.5 | 2015-10-20 | 2015-10-20 | Prabhjot Singh | Completed
|  |  |  | Self Testing | 4 | 2018-07-06 | 2015-10-19 | 4.5 | 2018-07-06 | 2015-10-19 | Prabhjot Singh | Completed
|  |  |  | Rework | 1 | 2015-10-20 | 2015-10-20 | 1.5 | 2015-10-20 | 2015-10-20 | Prabhjot Singh | Completed
|  |  |  | Code Peer Review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Rework | 1 | 2015-10-21 | 2015-10-21 | 1.5 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3.5 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 4.5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 1.5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 52 |  | Total Actual Hrs: | 36.3 |  |  |  | Completed
Airline Reservation System | 8 | Manage Flight Information | Analysis | Requirement Analysis | 2.1 | 2018-06-30 | 2018-06-30 | 3 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2018-06-30 | 2018-06-30 | 2.4 | 2018-06-30 | 2018-06-30 | C.Gowtham, A.Divya, T.Sirisha, M.Sindhu, M.Sai Anusha ,R.Kamatchi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.9 | 2018-07-03 | 2018-07-03 | 1 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Prabhjot Singh | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Prabhjot Singh | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Nafeez Virani | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Prabhjot Singh | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Nafeez Virani | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Prabhjot Singh | N/A
|  |  | Build | Coding | 10 | 2018-07-06 | 2015-10-19 | 11 | 2018-07-06 | 2015-10-19 | Prabhjot Singh | Completed
|  |  |  | Code Self Review | 4 | 2015-10-20 | 2015-10-20 | 3.5 | 2015-10-20 | 2015-10-20 | Prabhjot Singh | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 6 | 2018-07-06 | 2015-10-19 | Prabhjot Singh | Completed
|  |  |  | Rework | 2 | 2015-10-20 | 2015-10-20 | 2 | 2015-10-20 | 2015-10-20 | Prabhjot Singh | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Peer Testing | 1.5 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Nafeez Virani | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Rework | 1.5 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Prabhjot Singh | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 3.5 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 64 |  | Total Actual Hrs: | 46.6 |  |  |  | Completed
Airline Reservation System | 9 | Generate Reports | Analysis | Requirement Analysis | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2018-06-30 | 2018-06-30 | 2.4 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Rahul Yadav | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2015-10-15 | 2018-07-05 | Rahul Yadav | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Rahul Yadav | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Pritika Sharma | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Rahul Yadav | N/A
|  |  | Build | Coding | 11 | 2018-07-06 | 2015-10-19 | 9 | 2018-07-06 | 2015-10-19 | Rahul Yadav | Completed
|  |  |  | Code Self Review | 3 | 2015-10-20 | 2015-10-20 | 2 | 2015-10-20 | 2015-10-20 | Rahul Yadav | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 6 | 2018-07-06 | 2015-10-19 | Rahul Yadav | Completed
|  |  |  | Rework | 2 | 2015-10-20 | 2015-10-20 | 2 | 2015-10-20 | 2015-10-20 | Rahul Yadav | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Rework | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3.2 | 2015-10-23 | 2015-10-23 |  | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 3 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 63.6 |  | Total Actual Hrs: | 40.4 |  |  |  | Completed
Airline Reservation System | 10 | View Flight Occupancy | Analysis | Requirement Analysis | 1.8 | 2018-06-30 | 2018-06-30 | 1.8 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2.4 | 2018-06-30 | 2018-06-30 | 2.4 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Preparing QFB | 1.2 | 2018-06-30 | 2018-06-30 | 1.2 | 2018-06-30 | 2018-06-30 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 0.8 | 2018-07-03 | 2018-07-03 | 0.8 | 2018-07-03 | 2018-07-03 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  | Design | Unit Test Plan Preparation | 6 | 2018-07-04 | 2018-07-04 |  | 2018-07-04 | 2018-07-04 | Rahul Yadav | N/A
|  |  |  | LLD Preparation | 5 | 2018-07-05 | 2018-07-05 |  | 2018-07-05 | 2018-07-05 | Rahul Yadav | N/A
|  |  |  | UTP Review | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Pritika Sharma | N/A
|  |  |  | UTP Rework | 2 | 2018-07-04 | 2018-07-05 |  | 2018-07-04 | 2018-07-05 | Rahul Yadav | N/A
|  |  |  | LLD Review | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Pritika Sharma | N/A
|  |  |  | LLD Rework | 2.5 | 2018-07-05 | 2018-07-06 |  | 2018-07-05 | 2018-07-06 | Rahul Yadav | N/A
|  |  | Build | Coding | 11 | 2018-07-06 | 2015-10-19 | 9 | 2018-07-06 | 2015-10-19 | Rahul Yadav | Completed
|  |  |  | Code Self Review | 3 | 2015-10-20 | 2015-10-20 | 2 | 2015-10-20 | 2015-10-20 | Rahul Yadav | Completed
|  |  |  | Self Testing | 6 | 2018-07-06 | 2015-10-19 | 6 | 2018-07-06 | 2015-10-19 | Rahul Yadav | Completed
|  |  |  | Rework | 2 | 2015-10-20 | 2015-10-20 | 2 | 2015-10-20 | 2015-10-20 | Rahul Yadav | Completed
|  |  |  | Code Peer Review | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Peer Testing | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Pritika Sharma | Completed
|  |  |  | Test Result review | 1 | 2015-10-21 | 2015-10-21 | 1 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Rework | 2 | 2015-10-21 | 2015-10-21 | 2 | 2015-10-21 | 2015-10-21 | Rahul Yadav | Completed
|  |  |  | Code Integration | 3 | 2015-10-23 | 2015-10-23 | 3.2 | 2015-10-23 | 2015-10-23 |  | Completed
|  |  |  | Integration Testing | 1 | 2015-10-23 | 2015-10-23 | 1 | 2015-10-23 | 2015-10-23 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Rework | 4 | 2015-10-23 | 2015-10-24 | 3 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Test Result review | 1.4 | 2015-10-23 | 2015-10-24 | 2 | 2015-10-23 | 2015-10-24 | K.Yaswanth,D.Lakshmi Nagaratnam, K.NavyaSantoshi,S.Shruthi,K.S.Charumathi | Completed
|  |  |  | Total Planned Hrs : | 63.6 |  | Total Actual Hrs: | 40.4 |  |  |  | Completed
|  |  |  | Tot Planned Hrs | 9.6 |  | Tot Act Hrs | 9.6